StressFreeClaim.ai

Production Launch Plan

Prepared for Deskar 6 LLC  •  Recommended scope for approval  •  July 28, 2026

| RECOMMENDATION | Launch a counsel-cleared private pilot with durable intake, authenticated staff access, and an operational claims queue. Keep contracts, fees, insurer filing, voice, and CRM out. |
| --- | --- |

# Executive decision

Phase 1 is complete. The next release should be a narrow production-grade intake and operations product—not a broader automation platform. The fastest responsible route to market is a private pilot in counsel-cleared states.

Preserve the proven homeowner utterance → gaps → review experience.

Add durable storage, authenticated staff access, a claims queue, notifications, auditability, and production operations.

Exclude contracts, fee language, insurer filing, voice, CRM, and partner tools from launch.

# Why the original plan changes

The original Phase 2 correctly called for persistent claims and an internal view, but its one-to-two-week estimate describes visible features rather than everything required to accept real homeowner data. Today, drafts contain personal information in a browser cookie, submitted claims use ephemeral SQLite storage, there is no authentication, and the repository constitution intentionally prohibits production data and security work.

| PROMOTION RULE | Carry the validated intake UX forward. Replace the prototype storage, identity, security, and operations substrate under a separate production track and acceptance gate. |
| --- | --- |

# Launch promise

“Tell us what happened. A member of our team will review your information and contact you about next steps.”

Until counsel and operations approve otherwise, do not promise that a claim has been filed, that the company will represent the homeowner, that an affiliate will perform repairs, or that a fee will be waived.

# Launch scope

## Homeowner experience

Mobile-first guided intake with a server-side, expiring draft; the browser cookie carries only a random continuation token.

State eligibility against an administratively controlled allowlist.

Clear consent and privacy disclosure, full review and correction, and a truthful submission receipt.

Email confirmation plus calm recovery for expired drafts, duplicates, service failures, and unsupported states.

## Staff experience

Authenticated staff access with approved users, server-side roles, and MFA support.

Claims queue with status, state, claimant, date of loss, insurer, submitted time, assignment, search, and filters.

Claim detail, internal notes, assignment, and status workflow: new, reviewing, contacted, qualified, closed, duplicate.

Audit-recorded access, material changes, and authorized CSV exports.

## Platform and operations

Managed PostgreSQL, migrations, backups, and separate development, preview, and production environments.

Transactional email, structured logs, error monitoring, uptime checks, and personal-data redaction in telemetry.

Rate limiting, secure headers, request protections, server-side validation, retention/deletion procedures, and environment-managed secrets.

A named operator reviews the pilot queue every business day.

# Explicitly out of scope

Public-adjuster or construction contracts, e-signatures, and cancellation-window workflows.

Fee calculations, fee waivers, referral economics, or affiliate financial language.

Automated insurer calls or electronic claim filing; voice capture, transcription, or recording.

Payments, contractor portal, CRM sync, native apps, homeowner accounts, and multi-tenant organizations.

# Recommended delivery sequence

| Stage | Work | Target | Exit signal |
| --- | --- | --- | --- |
| 0 | Paper & operations | 2–5 business days, parallel | States, copy, privacy, owners, signed SOW |
| 1 | Production foundation | 3–5 engineering days | Durable data, auth, audit, environments |
| 2 | Launch slice | 5–8 engineering days | Intake, eligibility, queue, workflow, notifications |
| 3 | Hardening & release | 3–5 engineering days | Security, restore, QA, training, runbooks |
| Pilot | Controlled private pilot | 2 weeks | Manual review, metrics, twice-weekly decisions |

Recommended target: roughly three engineering weeks to a controlled pilot, subject to the legal, privacy, operational, and release gates—not a calendar-only promise.

# Workstream outcomes

## Gate 0 — Paper & operations

Pilot states, approved copy, receiving entity, privacy and retention decisions, staff list, queue owner, support promise, incident contacts, signed MSA/SOW, and client-owned production accounts.

## Workstream 1 — Foundation

A staff-only production shell authenticates correctly, stores synthetic claims durably, separates environments, and emits traceable audit events.

## Workstream 2 — Launch slice

The full mobile intake through staff follow-up works with synthetic data, including eligibility, consent, idempotency, status, assignment, notes, and notifications.

## Workstream 3 — Hardening

Authorization, accessibility, cross-browser and failure-mode QA, backup restore, telemetry redaction, incident rehearsal, staff training, and end-to-end launch rehearsal all pass.

## Private pilot

Controlled traffic in approved states, manual review of every submission, and twice-weekly review of completion, contact time, qualification, duplicates, support incidents, and abandonment.

# Launch acceptance gates

A submitted claim survives deployment, restart, and a successful database restore rehearsal.

Personal information is absent from the browser draft cookie and client-visible logs.

Anonymous users cannot read claims; unauthenticated staff cannot access protected surfaces.

Staff roles are enforced server-side for every protected read and write.

Every persisted homeowner field is visible and correctable before submission.

Duplicate submissions create one claim and one notification set.

Unsupported states cannot submit a production claim.

Notification failures are retried safely and visible to operators.

Claim access, exports, assignments, status changes, and notes generate audit events.

Backups, privacy, retention, deletion, monitoring, and incident response have named owners and rehearsed procedures.

Production copy contains no unapproved filing, representation, contractor, or fee promise.

The prototype remains a separate demo; production carries a pilot label and support contact.

# Suggested production architecture

Application: Keep Next.js, TypeScript, Tailwind, and Vercel.

Data: Use managed PostgreSQL and retain Prisma initially to minimize migration risk.

Identity: Use a managed provider with server-side sessions, staff allowlisting, roles, and MFA support.

Email: Use a transactional provider with delivery events and idempotent sending.

Monitoring: Use error monitoring and structured logs with deliberate personal-data redaction.

Extraction: Keep deterministic local parsing authoritative. The bounded model pass stays optional and cannot block or overwrite local values.

# Decisions needed from Deskar 6 LLC

Pilot states and the counsel who approved them.

Exact public-facing entity and brand.

Named staff users and the pilot queue owner.

Response-time promise to homeowners.

Privacy/retention owner and deletion contact.

Whether policy number and deductible should remain optional or be collected at all.

Desired pilot start date and expected weekly claim volume.